## Cover
QA Report
Sprint | : | 1
Project | : | DRIVER (Data for Road Incident Visualization Evaluation and Reporting)
Build | : | 1
Date | : | 2023-09-25
Reporter | : | Nigah Hossain

## Release Summary
Project Name Release Summary Report
Release Info |  | Browser & Device List
Release Name | 1 | # | Desktop web Browser | Version
Version Name | 1 | 1 | Chrome | 116.0.5845.188
Release Topic | Log in, Dashboard, My Account, Manage Duplicate Records, Map, Record List, Add a record
Start Date | 2023-09-25
End Date | 2023-09-27
QA Release Date | 2023-09-27
Release Status | N/A
Released By | Nigah Hossain
Prepared By | Nigah Hossain
Verified By | Abdul Quadir
Executed Test Type:
1 | Functional
2 | UI
Non Executed Test Type:
1 | Regression
2 | Security
3 | Retesting
4 | Reliability
5 | Usability
6 | Performance
7 | Device compatibility
8 | Non functional
9 | Android/IOS
10 | Database
11 | Integration
12 | User Acceptance

## Functionality Verification
Project Name Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | TL Comment | QA Comment
1 | Log in | Yes | Yes | NG |  | #479832 #479846
2 | Dashboard | Yes | Yes | NG |  | #479791 #479794
3 | My Account | Yes | Yes | OK
4 | Manage Duplicate Records | Yes | Yes | NG |  | #479809
5 | Map | Yes | Yes | NG |  | #479814
6 | Record List | Yes | Yes | NG |  | #479811 #479836
7 | Add a record | Yes | Yes | NG |  | #479569 #479839
[N.B: We have checked all screens and found some major and minor issues, these are posted in Redmine]

## Graphical Report
Test Case Execution Report
| Build Version No: | V-1.0
| Total Test cases: | 127
| Test Environments (Browsers): | 1
| Total Executable test cases: | 127
| Test Cases Executed: | 126
| Passed: | 113
| Failed: | 13
| NE: | 0
| NA: | 1
| WIP: | 0
| Total Reported Bugs : | 10
| New | 10
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 2
| Open | 6
| Fixed | 1
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 0
| Critical | 0
| Major | 2
| Minor | 6
| Trivial | 2
| Total: | 10
| Reported Bugs : (All Sprints) | 10
| New | 10
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 0
| Medium | 2
| High | 7
| Urgent | 1
| Immediate | 0
| Total: | 10
Step-2: Sprint#1 Bug summary
Step-2: Sprint#1 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint# Bug List
Bug Type | Quantity
UI: | 3
Functional: | 7
Total: | 10
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479791 | [V-1.0][Dashboard] In the Dashboard page, the contents are getting distorted while resizing the window. | New | High | Minor
2 | https://redmine.bjitgroup.com/redmine/issues/479814 | [V-1.0][Map] The 'Clear Filters' option is placed just beside the Filter Bar and the Save Filters, Add a record are placed under the user email. | New | Normal | Trivial
3 | https://redmine.bjitgroup.com/redmine/issues/479846 | [V-1.0][Log in] Error message about inputting only password is shown while signing in keeping both fields empty. | New | High | Minor
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479569 | [V-1.0][Add a record] In ARF (Accident Report Form), "NUMBER OF DRIVER CASUALTIES" field allows value at most 100. | New | High | Minor
2 | https://redmine.bjitgroup.com/redmine/issues/479832 | [V-1.0][Log in] While attempting to sign in with wrong credentials for multiple times, the system does not limit the total number of unsuccessful Sign-in attempts. | New | High | Minor
3 | https://redmine.bjitgroup.com/redmine/issues/479794 | [V-1.0][Dashboard] No Black Spot is spotted after redirecting to the Map from the 'Black Spots by Severity' section and checking the 'BLACKSPOTS' option. | New | High | Major
4 | https://redmine.bjitgroup.com/redmine/issues/479809 | [V-1.0][Manage Duplicate Records] After clicking on 'Manage Duplicate Records', the 'Potential Duplicate Records' page does not load any record. | New | Urgent | Major
5 | https://redmine.bjitgroup.com/redmine/issues/479811 | [V-1.0][Record List] In the Filter Bar, the 'Occurred Date' format is Date/Month/Year instead of Month/Date/Year. | New | Normal | Trivial
6 | https://redmine.bjitgroup.com/redmine/issues/479836 | [V-1.0][Record List] In the Filter Bar, there is no separate field for Driver sex and Passenger sex. | New | High | Minor
7 | https://redmine.bjitgroup.com/redmine/issues/479839 | [V-1.0][Add a record] In ARF (Accident Report Form), 'DRIVER AGE' field allows value at most 99. | New | High | Minor
Functional Bugs:
Step-2: Sprint#3- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 127 | 10 | 0 | 0

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 | 24 | 10 | 41.67% | 41.67%